## Sheet1
Thunderbird Irrigation Water Delivery District #1
Five Year Capital Improvement Plan
1) 1st Phase 2016-2017(4550'-4 Phases Total)
Distribution Line Replacement | Linear Ft. | Price | Estimate Total | Complete items | Fund Plan
Well Site to Lateral Replacement (Complete) | 575 | 38.75 | 22281.25 | 22281.25
Replace Valve on Lateral #2 (Complete 4/2/18) |  | 2492.73 | 2492.73 | 2492.73
Repairs to Lateral #1 (Complete)
Signage, Tractor Repair, Paint Tank-(Complete 6/19) |  | 16044 | 16044 | 16044
2) 2nd Phase 2017-2018
Replacement of Distribution Line |  |  |  |  | Remove
Replace Lateral #2 | 1325 | 38.75 | 51343.75 | 51343.75 | Remove
Replace Fencing (Complete 03/18) |  | 12485.72 | 12485.72 | 12485.72
Lighting at Well Site |  | 200 | 200 |  | Remove
3) 3rd Phase 2018-2019
Replacement of Distribution Line
Lateral #2 & #3 (Revised plan 2024/25) | 1325 | 38.75 | 51535.75 | 51535.75
Replace Lateral #3 (Revised plan 2024/25)
Replace shut off valves & Meters (1/3 Done)
Reline Tank Interior (Complete 5/19) |  |  | 39970 | 39970
4) 4th Phase2019-2020
Replacement of Distribution Line
Lateral #3 & #4 (Revised plan 2024/25) | 1325 | 50 | 66250 |  | Remove
Replace Lateral #4 (Revised plan 2024/25) |  |  |  |  | Remove
Gravel Wellsite (Revised plan 2024/25) |  | 2500 | 2500
5) 5th Phase 2019/2020
Replacement of District shed roof (Revised 2024/25) |  | 500 | 500 |  | Remove
Meter Change-out |  | 5000 | 5000
(10) meters per yr. |  | 750 | 7500
Install Flushing valves @ ea. Lateral end (Lat1 Complete 2023) |  | 250 | 1000 | 1000
6) Emergency/ Contingency funds 2019-2021 |  |  |  |  | 120000
2019/2020 |  | 85000
2020/2021 |  | 35000
7) 6th Phase 2023/2024
Lateral & Park Clean-up/Maint (Complete 6/2023) |  | 2217 |  | 2217
Install Flushing valves @ ea. Lateral end (Revised 2019/2020)
Well scoping (Revised 2024/25)
Repair Lateral 1 (Complete 3/24) |  | 1100 |  | 1100
8) 7th Phase 2024/2025 |  |  |  |  | 82200
Install Flushing valves @ ea. Lateral end 2,3,4 |  |  | 3200
Lateral Clean-up/Maint |  | 3000
Replace shed (Revised 2019/2020) |  | 600 | 1000
Well scoping & piping replacement |  | 48000 | 60000
Tank Inspection & Maintenance |  | 5000 | 15000
Total | 4550 | 220305.7 | 358303.2 | 200470.2 | 202200
Rev 05/2024